Risk register

| Risk | Description | Likelihood | Severity | Mitigation |
| --- | --- | --- | --- | --- |
| Literature Accessibility | Some key studies or data may be behind paywalls or restricted. | Medium | Medium | Use open-access resources and contact authors for full texts when necessary. |
| Complexity of Techniques | The complexity of implementing certain optimisation techniques may extend beyond the project’s timeline. | Medium | High | Experiments shall be initiated using existing open-source solutions, with a focus on methods that do not require custom development. |
| Time Management | The experimental phase may prove time-consuming. | High | Medium | Develop a detailed project timeline to ensure critical milestones are met. Prioritise theoretical work if experimental progress falls behind. |
| Variability in Code Generation Results | Performance of techniques may vary with task complexity, leading to inconclusive results. | Medium | High | Select a diverse set of benchmark tasks covering various complexities and use statistical methods for robust analysis. |
| Challenges in Data Quality | Optimisation techniques depend on high-quality datasets; poor data can yield misleading results. | Medium | High | Vet benchmark datasets for quality and relevance; follow best practices in data collection and preprocessing. |
| Overfitting in Experimental Evaluation | Techniques may perform well on the benchmark dataset but not generalise to real-world scenarios. | High | Medium | Apply cross-validation and test on multiple datasets, reporting metrics for both training and unseen data. |